RedDust Backend

Development Roadmap

AI-Powered Voice Wellness Companion — Gemini Live Backend

Deadline: 4 September 2026

# About This Document

This is the official step-by-step backend development roadmap for RedDust. It covers every task that needs to be completed before the 4 September 2026 deadline. Steps owned by the audio relay / WebSocket developer are excluded — this document covers only the RAG pipeline, database schema, function handlers, preference extraction, music recommendation engine, and session lifecycle work.

Each step includes what to do, why it is needed, how to verify it is working, which files are affected, and any important notes or constraints.

## System Architecture (High Level)

RedDust is a real-time voice wellness companion powered by Gemini Live. The backend handles five major responsibilities:

• RAG Knowledge Service — embeds wellness documents into pgvector on Supabase; retrieves grounded answers when Syan (the AI persona) needs factual backing.

• PostgreSQL Application Database — stores users, sessions, conversations, transcript segments, soul scores, music preferences, and recommendations.

• Function Handlers — three callable functions exposed to Gemini Live: fetch_user_context, get_music_recommendation, retrieve_anodiam_knowledge.

• Preference & Wellbeing Engine — extracts music preferences from conversation turns; computes soul scores across 32 wellbeing dimensions.

• Music Recommendation Engine — uses stored preferences + current soul score + YouTube Data API to find and verify personalised tracks.

## Technology Stack

| Layer | Technology |
| --- | --- |
| Web Framework | FastAPI (Python) |
| Voice AI | Gemini Live (google-genai SDK) |
| LLM / Embeddings | gemini-2.0-flash, gemini-embedding-001 (1536-dim) |
| Vector DB | pgvector on Supabase (HNSW index, cosine similarity) |
| App Database | PostgreSQL on Supabase via asyncpg |
| Task Queue | ARQ (Redis-backed async worker) |
| HTTP Client | httpx (async) |
| Music Source | YouTube Data API v3 |
| Doc Parsing | python-docx, openpyxl |
| Env / Deps | uv, pyproject.toml |
| Schema | RedDust schema on Supabase |

## Active Deviations from Original Plan

• Reranker (reranker.py) is written and present in the codebase but intentionally bypassed in the live pipeline due to free Gemini API quota limits. The RAG pipeline flows: retriever → synthesizer directly. The reranker can be re-enabled when quota allows — no code changes needed, only service.py routing.

• EMBEDDING_DIM is locked at 1536 — this matches Supabase pgvector column (vector(1536)). Do not change to 3072 without a DB column migration.

• parsers.py uses a generalised heading-detection heuristic (_is_heading_line) instead of Word heading styles, because all source .docx files use Normal paragraph style throughout with zero formatting signals.

# Phase 1 — RAG Knowledge Service

Steps 1–8 | Status: COMPLETE

### Step 1: Install RAG Dependencies

| Step | 1 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Add google-genai, pgvector, openpyxl, python-docx, asyncpg, httpx to pyproject.toml using uv add. Confirm all imports resolve. |
| Why we need it | The RAG pipeline cannot function without these libraries. google-genai provides the Gemini embedding and synthesis API. pgvector provides the Python adapter for the vector column. openpyxl and python-docx parse the knowledge base source files. asyncpg is the async PostgreSQL driver used throughout the backend. |
| How to verify | python -c "import asyncpg; import pgvector; import openpyxl; import docx; print('all good')" → prints 'all good'. |
| Files | backend/requirements.txt |
| Notes | sentence-transformers was intentionally skipped — it pulls PyTorch+CUDA (~1.5 GB). Reranking is handled by Gemini Flash Lite instead. |

### Step 2: File Parser Layer

| Step | 2 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/parsers.py with parse_scientific_research() and parse_traditional_wisdom() functions. Each reads a .docx file and returns a list of text chunks with metadata (filename, section name, RedDust_relevance). |
| Why we need it | The RAG system cannot embed raw .docx files — they must be converted to clean text chunks first. The parser is the entry point of the ingestion pipeline. Chunking must respect document structure (research entries, cultural wisdom sections) so each embedded chunk is semantically coherent and retrievable as a self-contained piece of knowledge. |
| How to verify | Run parse_scientific_research() on ScientificResearchKnowledgeBase.docx → 3 chunks, all with RedDust_relevance metadata. Run parse_traditional_wisdom() on TraditionalWisdom.docx → 20 chunks, 15 with RedDust_relevance. |
| Files | backend/app/services/rag/parsers.py |
| Notes | All source .docx files use Normal paragraph style throughout — there are no Word heading styles. Headings are detected by the _is_heading_line() heuristic: line length <= 80 chars, no sentence-ending punctuation, not a bullet or citation. ScientificResearch uses an additional year-in-parentheses regex for H1 detection. parse_soul_score_context() is deferred to Phases 14+ when the soul score schema is ready. |

### Step 3: Embedding Pipeline

| Step | 3 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/embedder.py. Implement embed_and_upsert(chunks, metadata, pool: asyncpg.Pool). This calls the Gemini text-embedding API (gemini-embedding-001, output_dimensionality=1536) to embed each chunk, then upserts into the anodiam_knowledge table on Supabase with content, embedding vector, metadata (JSONB), and domain columns. |
| Why we need it | This is the core ingestion step. Without embedding, there is nothing to search. Embeddings convert raw text into 1536-dimensional vectors that can be compared by cosine similarity. Upserting (not inserting) ensures re-running the ingestion script does not create duplicate rows — it updates existing chunks if content changes. |
| How to verify | Check Supabase Table Editor — anodiam_knowledge rows must have non-null embedding columns and correct JSONB metadata. |
| Files | backend/app/services/rag/embedder.py, backend/app/config.py, backend/.env |
| Notes | EMBEDDING_DIM = 1536 is locked to Rajanya's DB schema. normalize_embedding() must be called inside _embed_texts() before upserting. The .env file must not wrap values in quotes — asyncpg breaks on quoted connection strings. YOUTUBE_API_KEY must have a default in config.py to prevent startup crash even before the key is obtained. |

### Step 4: pgvector Table Setup on Supabase

| Step | 4 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Enable the pgvector extension on the Supabase project. Create the anodiam_knowledge table with columns: id (uuid), content (text), embedding (vector(1536)), metadata (jsonb), domain (text). Create a HNSW index with vector_cosine_ops on the embedding column. Add a unique index on (domain, content) to prevent duplicates. |
| Why we need it | pgvector is a PostgreSQL extension that adds a native vector column type and vector similarity operators. Without this table and extension, there is nowhere to store embeddings or run similarity searches. The HNSW index (Hierarchical Navigable Small World) is used instead of IVFFlat because it provides better recall and does not require a training step — it works on any dataset size from the start. |
| How to verify | Run: SELECT column_name, udt_name, atttypmod FROM information_schema.columns WHERE table_name='anodiam_knowledge' → confirms vector(1536). Run: \d anodiam_knowledge → confirms HNSW index present. |
| Files | (none — Supabase migration, no code files) |
| Notes | RLS (Row Level Security) is enabled on Supabase by default but is irrelevant here — the backend connects via the direct Postgres URL (SUPABASE_DB_URL) using asyncpg, which bypasses RLS entirely. WSL2 IPv6 routing issues are resolved by using the Supabase Session Pooler URL (IPv4) for SUPABASE_DB_URL. |

### Step 5: Vector Search / Retriever

| Step | 5 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/retriever.py. Implement retrieve(query: str, domain: str ¦ None, top_k: int = 20) -> list[dict]. This embeds the query using the same Gemini embedding model (gemini-embedding-001, output_dimensionality=1536), then runs a cosine similarity search on the anodiam_knowledge table filtered by domain, and returns the top_k results with content, similarity score, and metadata. |
| Why we need it | This is the search step. When Syan needs knowledge (e.g. the science behind breathwork), the retriever embeds the query and finds the most semantically similar chunks in the knowledge base. The domain filter ensures the search is scoped — e.g. only searching scientific_research chunks when the query is about research-backed techniques. |
| How to verify | Static analysis: all imports resolve, output_dimensionality=1536 is enforced in embed_query(). Functional test deferred to Step 8 (requires live DB). |
| Files | backend/app/services/rag/retriever.py |
| Notes | output_dimensionality=1536 must be passed in types.EmbedContentConfig — without it, the API returns full 3072-dim vectors that do not match the DB column. DEFAULT_TOP_K is set to 20 to give the synthesizer sufficient context even with the reranker bypassed. |

### Step 6: Reranker (Present but Bypassed)

| Step | 6 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/reranker.py. Implement rerank(query: str, chunks: list[dict], top_n: int) -> list[dict]. Uses Gemini Flash Lite to score each chunk's relevance to the query concurrently (asyncio.gather), sorts by score descending, and returns top_n chunks. |
| Why we need it | A reranker improves RAG quality by re-evaluating retrieved chunks with a more expensive relevance signal than cosine similarity. Cosine similarity finds chunks that are topically close but may not directly answer the query. The reranker, using an LLM, can assess actual answer relevance. This step must be built now so it can be activated later with a single routing change in service.py. |
| How to verify | Import test: from app.services.rag.reranker import rerank → no errors. Static analysis: _score_chunk() prompt and score parsing correct. |
| Files | backend/app/services/rag/reranker.py |
| Notes | CURRENTLY BYPASSED — free Gemini API quota limits make concurrent LLM calls per chunk too expensive. service.py routes retriever → synthesizer directly. To re-enable: update service.py to insert reranker between retriever and synthesizer. No reranker.py changes needed. |

### Step 7: Synthesizer (Response Formatter)

| Step | 7 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/synthesizer.py. Implement synthesize(query: str, chunks: list[dict]) -> str. Calls Gemini Flash Lite with the retrieved chunks as context and the original query. The model returns a grounded, conversational answer. If chunks is empty, it returns a graceful fallback message. |
| Why we need it | The synthesizer is the final step of the RAG pipeline. Without it, the retrieved text chunks are just raw document excerpts — not useful for Syan to speak aloud. The synthesizer transforms them into a coherent, warm, persona-consistent response that Syan can deliver to the user as part of the voice conversation. |
| How to verify | Live test: synthesize(query, 2 real chunks) → correct grounded answer, correctly flags information not present in chunks. synthesize(query, []) → graceful fallback. Both pass. |
| Files | backend/app/services/rag/synthesizer.py |
| Notes | Model: gemini-2.0-flash or flash-lite (confirm current free quota model). The synthesizer must instruct the model to stay grounded — only answer from provided chunks, state clearly when something is not in context. Metadata['source'] will AttributeError if the JSONB metadata was stored as a string instead of a dict — this is linked to the embedder JSONB bug fixed in Step 3. |

### Step 8: End-to-End RAG Pipeline Wiring

| Step | 8 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/rag/service.py. Implement retrieve_anodiam_knowledge(query: str, domain: str ¦ None, pool: asyncpg.Pool) -> str. This orchestrates the full pipeline: retriever → (reranker, currently bypassed) → synthesizer → returns final text answer. Also create backend/app/services/functions/knowledge.py to wrap this as the Gemini Live function handler. |
| Why we need it | This step wires the individual RAG components into a single callable function. Without service.py, the retriever, reranker, and synthesizer are isolated modules with no orchestration. The function handler in knowledge.py is what Gemini Live actually calls when Syan decides to look up knowledge — it bridges the RAG service and the Gemini Live function-calling protocol. |
| How to verify | Run test_rag_e2e.py from the backend root. Ingest a sample .docx → confirm rows in Supabase anodiam_knowledge table → query with a matching question → confirm synthesized answer returned. All assertions pass. |
| Files | backend/app/services/rag/service.py, backend/app/services/functions/knowledge.py |
| Notes | Reranker is intentionally skipped in service.py (retriever → synthesizer). This deviation is logged. Verify anodiam_knowledge rows have non-null embeddings and JSONB metadata (not string) in Supabase Table Editor. |

# Phase 2 — Application Database Schema

Steps 9–10 | Status: PENDING (blocked on schema verification and migration)

### Step 9: Core PostgreSQL Schema Migration

| Step | 9 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Design and run migration_001 on Supabase. Create the core RedDust schema tables: app_user (id, display_name, locale, timezone, created_at), user_session (session_id, user_id FK, started_at, ended_at, status), conversation (conversation_id, session_id FK, user_id FK, sequence_no, started_at, ended_at), turn (turn_id, conversation_id FK, session_id FK, turn_no, started_at), emotional_patterns (id, user_id FK, pattern jsonb, recorded_at), soul_scores (id, user_id FK, score float, computed_at), wellbeing_deltas (id, user_id FK, session_id FK, delta float, recorded_at). All tables in the RedDust schema. |
| Why we need it | All backend features depend on this schema. Without it, nothing can be persisted — no sessions, no transcripts, no preferences, no soul scores, no music recommendations. This is the foundation every subsequent step builds on. Getting the schema right before building handlers avoids costly migrations later. |
| How to verify | psql or Supabase SQL editor: SELECT table_name FROM information_schema.tables WHERE table_schema='RedDust' ORDER BY table_name → all tables present. INSERT test row into each table → no constraint errors. |
| Files | backend/migrations/migration_001_core_schema.sql |
| Notes | All tables must be in the RedDust schema (not public). Foreign keys must be consistent. session_id and conversation_id are referenced by many downstream tables — define them carefully. Discuss soul_score table structure early — it is referenced by the dashboard view used in fetch_user_context. |

### Step 10: asyncpg Connection Pool

| Step | 10 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/db/pool.py with a create_pool() function that initialises an asyncpg connection pool using SUPABASE_DB_URL from config.py. Wire the pool into FastAPI's lifespan events in main.py: create on startup, attach to app.state.pool, close on shutdown. |
| Why we need it | asyncpg is the async PostgreSQL driver. Every database operation in the backend (reading user data, writing transcripts, upserting preferences) goes through this pool. Without it, none of the function handlers or service modules can query or write to the database. The lifespan pattern ensures the pool is always available when requests arrive and is cleanly closed when the server shuts down. |
| How to verify | Start FastAPI server → no startup errors → make a test request that uses app.state.pool → confirm query returns expected data. |
| Files | backend/app/db/pool.py, backend/app/main.py |
| Notes | SUPABASE_DB_URL must point to the Session Pooler URL (IPv4) — not the direct DB URL — to avoid WSL2 IPv6 routing failures. The pool should set min_size=2, max_size=10 as reasonable defaults for development. |

# Phase 3 — Function Handlers

Steps 11–13 | Step 11 partially done, Steps 12–13 pending DB

### Step 11: Function Call Dispatcher

| Step | 11 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/function_dispatcher.py. Implement dispatch(function_call, pool, user_id, session_id, ...) which matches the Gemini Live function call name and routes it to the correct handler: fetch_user_context → user_context.py, get_music_recommendation → music.py, retrieve_anodiam_knowledge → knowledge.py. Returns a Gemini Live FunctionResponse. |
| Why we need it | Gemini Live sends function call events when Syan decides to invoke a capability (look up knowledge, fetch user history, recommend music). Without a dispatcher, these events are ignored and Syan cannot access any external data. The dispatcher is the bridge between Gemini Live's function-calling protocol and the backend handler implementations. |
| How to verify | Import test: from app.services.function_dispatcher import dispatch → no errors. Static analysis: all three routes present and correct. |
| Files | backend/app/services/function_dispatcher.py, backend/app/services/functions/__init__.py, backend/app/services/functions/user_context.py (placeholder), backend/app/services/functions/music.py (placeholder), backend/app/services/functions/knowledge.py |
| Notes | Placeholder files for all three handlers were created to resolve import errors at startup. The actual handler implementations are in Steps 12, 13, and 16. |

### Step 12: get_music_recommendation Handler (Basic)

| Step | 12 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Implement backend/app/services/functions/music.py. handle_get_music_recommendation(args, user_id, session_id, pool) calls YouTube Data API v3 with a mood-to-query mapping (e.g. anxious → 'calming meditation music'). Returns the top result's title and URL as a FunctionResponse dict. YOUTUBE_API_KEY must be set in config.py and .env. |
| Why we need it | This is the first functional version of music recommendation — it gives Syan the ability to suggest music immediately, before the full preference engine is built. A simple mood→query mapping is sufficient for early testing. It also validates the YouTube API key and quota setup before the more complex recommendation engine (Phase 8) is added. |
| How to verify | Call handle_get_music_recommendation({'mood': 'anxious'}) → returns {title: str, url: str} with a valid YouTube URL. |
| Files | backend/app/services/functions/music.py, backend/app/config.py, backend/requirements.txt (httpx) |
| Notes | YouTube API key must be created via Google Cloud Console. Enable YouTube Data API v3. Free quota: 10,000 units/day. A search request costs 100 units. Get the key before testing. httpx must be in requirements.txt. |

### Step 13: fetch_user_context Handler

| Step | 13 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Implement backend/app/services/functions/user_context.py. handle_fetch_user_context(args, user_id, pool) queries the RedDust schema and returns: (1) app_user display_name, locale, timezone; (2) latest soul score snapshot for this user (top 8 dimensions); (3) all user_music_preference rows; (4) last 3 session_summary rows; (5) latest quarterly user_period_summary. Returns as a structured dict FunctionResponse. |
| Why we need it | Syan calls fetch_user_context at the start of every session to personalise the conversation. Without it, every session starts cold — Syan treats a long-time user the same as a brand new one, ignoring their history, preferences, and emotional patterns. This function is what makes RedDust feel like it remembers the user. |
| How to verify | Test with a seeded user → all 5 sections populated in the response. Test with a new user with no history → returns defaults/nulls gracefully without crashing. |
| Files | backend/app/services/functions/user_context.py |
| Notes | Blocked on Steps 9–10 (schema deployed and asyncpg pool running). The dashboard view v_user_dashboard_soul_score referenced here must be created as part of the soul score schema (Phase 7). |

# Phase 4 — Schema Additions (Preferences & Transcripts)

Steps 14–15 | Status: PENDING

### Step 14: Additional Tables Migration

| Step | 14 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Write and run migration_002_preferences_transcript.sql. Create three new tables in the RedDust schema: (1) user_music_preference — stores extracted music preferences per user with columns: user_id (FK), preference_type (genre/artist/decade/language/life_situation), preference_value (TEXT), confidence (NUMERIC 0–1), source, first_observed_at, last_confirmed_at, override_count. PK on (user_id, preference_type, preference_value). (2) preference_extraction_log — audit trail of every extraction event with session/conversation/turn FK references. (3) transcript_segment — stores every utterance from the conversation with speaker (user/syan), text, segment_index, and timestamps. Index on (session_id, segment_index) and (conversation_id, segment_index). |
| Why we need it | These three tables are the foundation of the intelligence layer. transcript_segment is the raw data source for everything — preference extraction, soul scoring, session summarisation. user_music_preference is the persistent memory of what the user likes, built up across many sessions. preference_extraction_log is the audit trail that lets us debug and improve extraction quality over time. Without these tables, the backend has no memory beyond a single session. |
| How to verify | psql: SELECT table_name FROM information_schema.tables WHERE table_schema='RedDust' → all 3 new tables visible. INSERT test row into each → no constraint errors. |
| Files | backend/migrations/migration_002_preferences_transcript.sql |
| Notes | The user_music_preference PK is a composite key on (user_id, preference_type, preference_value) — this means one user can have multiple values per type (e.g. genre=classical AND genre=jazz). Upsert logic must match this PK correctly. |

### Step 15: Schema Connectivity Verification

| Step | 15 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Write backend/scripts/check_schema.py. Connect via asyncpg using SUPABASE_DB_URL. Query: SELECT table_name FROM information_schema.tables WHERE table_schema='RedDust' ORDER BY table_name. Print the list. Confirm all expected tables are present: app_user, user_session, conversation, turn, emotional_patterns, soul_scores, wellbeing_deltas, user_music_preference, preference_extraction_log, transcript_segment, and any Rajanya-defined soul score tables. |
| Why we need it | Before building any handler that reads from or writes to the DB, we must confirm that the asyncpg pool can actually reach the database and that all expected tables are present. Debugging a function handler that silently fails because a table doesn't exist is far harder than a dedicated 30-second schema check up front. |
| How to verify | python scripts/check_schema.py → prints all RedDust.* table names. No connection errors. |
| Files | backend/scripts/check_schema.py |
| Notes | Run this script every time a new migration is deployed. If a table is missing, fix the migration before proceeding. |

# Phase 5 — Preference Extraction

Steps 16–17 | Status: PENDING

### Step 16: Per-Turn Preference Extractor

| Step | 16 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/services/preference_extractor.py. Implement extract_preferences_from_turn(turn_text, user_id, session_id, conversation_id, turn_id, pool). Call Gemini Flash with a tight prompt: given one turn of user speech, return a JSON list of {preference_type, preference_value, confidence} — but ONLY for high-confidence, explicit statements (I love / I hate / I never / I always). Threshold: confidence >= 0.8 to write. Write to preference_extraction_log and upsert into user_music_preference. Fire-and-forget — caller uses asyncio.create_task. Never blocks the audio relay loop. |
| Why we need it | Music preference learning must happen in real time as the user speaks. If a user says 'I hate sad songs' mid-session, the recommendation engine should know this before the next recommendation request — not after the session ends. Per-turn extraction captures explicit high-confidence signals immediately. The fire-and-forget pattern ensures this never slows down the voice conversation. |
| How to verify | Unit test: turn_text='I really love 90s Bollywood and I hate sad songs' → 2 rows in preference_extraction_log, 2 upserts in user_music_preference. Unit test: 'What if someone liked jazz' (hypothetical) → 0 rows extracted. |
| Files | backend/app/services/preference_extractor.py |
| Notes | Must be strictly selective — only extract from explicit first-person statements. Hypotheticals, questions, and indirect references must be ignored. False positives corrupt the preference store and degrade recommendation quality. |

### Step 17: End-of-Session Batch Preference Extractor

| Step | 17 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/services/preference_batch_extractor.py. Implement extract_preferences_from_session(session_id, user_id, pool). At session end, fetch all transcript_segment rows for the session ordered by segment_index, concatenate into a full transcript, and call Gemini Flash with the full context. The prompt asks for all preferences — including implicit and nuanced ones — with contradiction resolution (later statement wins). Returns JSON list of {preference_type, preference_value, confidence, evidence_quote}. Upsert into user_music_preference, overwriting per-turn entries if confidence is higher. Write all to preference_extraction_log with extraction_method='session_batch'. |
| Why we need it | Per-turn extraction misses nuanced preferences that only emerge across a full conversation — e.g. a user who mentions jazz three times casually but never says 'I love jazz' explicitly. The batch extractor reviews the whole session and can catch these patterns. It also resolves contradictions: if the user said 'I like jazz' in turn 2 but 'actually I prefer classical' in turn 8, the batch extractor ensures the DB stores classical, not jazz. |
| How to verify | Test with a multi-turn transcript where the user changes their preference mid-session → user_music_preference shows the later preference, not the earlier one. preference_extraction_log shows both entries with correct extraction_method values. |
| Files | backend/app/services/preference_batch_extractor.py |
| Notes | This is called at session end via asyncio.create_task — fire-and-forget. The WebSocket disconnect handler must not await it. The ARQ soul score job also calls this function — ensure it is safe to call more than once per session (idempotent upserts). |

Phase 6 — Track Search & Verification

Steps 18–19 | Step 18 done, Step 19 pending

### Step 18: Track Verifier (YouTube Data API)

| Step | 18 of 26 |
| --- | --- |
| Status | COMPLETE |
| What to do | Create backend/app/services/track_verifier.py. Implement verify_and_fetch_track(query: str, pool: asyncpg.Pool) -> dict ¦ None. Two-call YouTube API strategy: (1) search endpoint — q=query, type=video, part=snippet, maxResults=5, regionCode=IN. (2) videos endpoint — fetch part=status,contentDetails for top 3 results. Filter: privacyStatus=public, embeddable is not false, not region-restricted for IN. Parse ISO 8601 duration to milliseconds. Return: {provider, provider_track_id, title, channel_title, thumbnail_url, duration_ms, track_url} or None. Add TTLCache (256 entries, 1hr TTL) keyed on query string. Handle 403 quotaExceeded gracefully — return None. |
| Why we need it | The basic music handler (Step 12) returns whatever the YouTube search API gives first. That is risky — the first result might be a private video, age-restricted, or unavailable in India. The verifier adds a quality gate: it checks embeddability and regional availability before returning a track. The cache prevents repeated API calls for the same query within a session, protecting the daily quota. |
| How to verify | Static analysis: imports resolve, two-call logic correct. Functional test deferred until YouTube API key is active. Simulate 403 response → function returns None without raising. |
| Files | backend/app/services/track_verifier.py, backend/app/config.py |
| Notes | YOUTUBE_REGION_CODE defaults to 'IN', YOUTUBE_LANGUAGE defaults to 'en' — both configurable in config.py. The search endpoint alone does not return embeddability status — the second videos endpoint call is required. |

### Step 19: YouTube API Key Setup & Cache Verification

| Step | 19 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create a YouTube Data API v3 key in Google Cloud Console. Enable the API. Add the key to .env as YOUTUBE_API_KEY. Test: call verify_and_fetch_track with a real query → confirm a valid track is returned. Test cache: call with same query twice → second call hits cache (log confirms no API call). Test quota error: simulate 403 → function returns None cleanly. |
| Why we need it | The track verifier is written but cannot be tested without an API key. This step activates it. Quota monitoring is also important — the free tier gives 10,000 units/day, and a search request costs 100 units, meaning a maximum of 100 searches per day. The cache is critical to staying within this limit during active sessions. |
| How to verify | Two identical queries → second call is cache hit. Simulate 403 → returns None. Real query → returns {title, url, ...} dict. |
| Files | backend/.env, backend/app/config.py, backend/app/services/track_verifier.py |
| Notes | Use a Google account with billing enabled (even with $0 spend) to get higher quota limits if needed. Monitor quota usage in Google Cloud Console. |

# Phase 7 — Music Recommendation Engine

Steps 20–21 | Status: PENDING

### Step 20: Context-Aware Music Recommender

| Step | 20 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/services/music_recommender.py. Implement build_music_recommendation_context(user_id, session_id, pool) → dict. Fetches: (1) all user_music_preference rows for the user, (2) latest soul score snapshot from v_user_dashboard_soul_score, (3) last 5 music recommendations + reactions (avoid recently disliked tracks). Implement recommend_tracks(user_id, session_id, conversation_id, turn_id, current_mood_hint, pool) → list[dict]. Calls Gemini Flash with the context dict + mood hint. Returns 2–3 {query_string, desired_outcome, rationale, target_dimensions[]} suggestions. Also calls retrieve_anodiam_knowledge for music-wellbeing evidence to ground recommendations in the knowledge base. |
| Why we need it | The basic music handler (Step 12) uses a fixed mood→query map with no memory of who the user is. The recommender engine makes music a genuine therapeutic tool — it knows the user listens to classical music, that their Calmness dimension is low today, and that they disliked the last track. Every recommendation becomes personalised and intentional, not random. |
| How to verify | Test with seeded user data (genre=classical, soul score with low Calmness) → recommend_tracks returns 2–3 query strings that reflect those preferences. All query strings are specific enough to pass to verify_and_fetch_track. |
| Files | backend/app/services/music_recommender.py |
| Notes | Blocked on Step 9 (DB schema) and soul score views being deployed. The v_user_dashboard_soul_score view must exist before this function can query it. |

### Step 21: Update Music Handler to Use Recommender

| Step | 21 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Update backend/app/services/functions/music.py. The updated handle_get_music_recommendation now: (1) calls build_music_recommendation_context() for preferences + soul score, (2) calls recommend_tracks() for 2–3 query strings with rationale, (3) calls verify_and_fetch_track() for each query string, (4) upserts verified tracks into music_track table, (5) writes music_recommendation rows with rank, rationale, and recommendation_context, (6) returns list of {title, url, thumbnail, duration, artist, rationale} as FunctionResponse to Gemini Live. |
| Why we need it | This upgrades the music function from a simple search to a full pipeline: personalised query generation → track verification → DB persistence → structured response. The rationale in each result is what Syan actually says to the user ('I chose this because it has a slow BPM which can help with the anxiety you mentioned'). Persisting recommendations in the DB enables reaction tracking and future preference learning. |
| How to verify | End-to-end: call handler with mood_hint='anxious' and a seeded user → returns 2–3 verified YouTube tracks with titles, URLs, and rationale. music_recommendation rows written to DB. |
| Files | backend/app/services/functions/music.py |
| Notes | This step depends on the music_track and music_recommendation tables existing in the schema (from Step 9 or a dedicated migration). Confirm these tables are defined before building. |

# Phase 8 — Transcript Segment Storage

Step 22 | Status: PENDING (depends on audio relay)

### Step 22: Transcript Writer

| Step | 22 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/services/transcript_writer.py. Implement write_transcript_segment(session_id, conversation_id, turn_id, segment_index, speaker, text, started_at, ended_at, pool) → None. Inserts a row into RedDust.transcript_segment. This is called from the audio relay loop (Anirban's code) each time an outputTranscription segment arrives from Gemini Live. Fire-and-forget via asyncio.create_task. For user-speaker segments, also fire-and-forget: asyncio.create_task(extract_preferences_from_turn(...)). |
| Why we need it | Every downstream intelligence feature — preference extraction, soul scoring, session summaries, batch extraction — depends on the transcript being persisted. Without this writer, all conversation content is lost when the session ends. The fire-and-forget pattern keeps the audio relay loop latency-free — storing a transcript segment must never delay the voice stream. |
| How to verify | After a test session: SELECT count(*) FROM RedDust.transcript_segment WHERE session_id=X → matches number of Gemini Live outputTranscription segments received. |
| Files | backend/app/services/transcript_writer.py |
| Notes | speaker must be either 'user' or 'syan' — no other values. segment_index must be monotonically increasing per session. This module is complete on your side; it only needs to be integrated once Anirban wires it into the audio relay loop. |

# Phase 9 — Soul Score & Wellbeing

Steps 23–24 | Status: PENDING

### Step 23: Conversation Dimension Scorer

| Step | 23 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Create backend/app/services/dimension_scorer.py. Implement score_conversation_dimensions(conversation_id, session_id, user_id, pool) → None. Fetches all transcript_segment rows for the conversation. Calls Gemini Flash with the full transcript and descriptions of the 32 wellbeing dimensions. Prompt: score each relevant dimension 0–100 with confidence and a one-line rationale. Returns JSON. Writes to conversation_dimension_score table (upsert). For high-confidence signals (confidence >= 0.75), also writes wellbeing_signal rows. Called at conversation end. |
| Why we need it | The soul score is RedDust's flagship feature — a holistic wellbeing metric built from 32 dimensions (Calmness, Resilience, Connection, etc.). Scoring individual conversations is the data collection step. Without per-conversation scores, there is nothing to aggregate into a session score or track over time. The 32-dimension approach means each conversation produces rich, nuanced data that reveals patterns the user may not be consciously aware of. |
| How to verify | Test with a seeded transcript showing anxiety → conversation_dimension_score has Calmness score < 50. wellbeing_signal has direction=-1 for Calmness. High-confidence signal written, low-confidence signal skipped. |
| Files | backend/app/services/dimension_scorer.py |
| Notes | Blocked on soul score schema (conversation_dimension_score, wellbeing_signal tables) being deployed as part of Step 9 migrations. Confirm table names and column definitions with Rajanya before writing insert queries. |

### Step 24: ARQ Job: Session Soul Score Computation

| Step | 24 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | Update backend/app/worker.py. Add ARQ job: compute_session_soul_score(ctx, user_id: str, session_id: str). This job: (1) calls CALL RedDust.refresh_session_dimension_scores(session_id) to aggregate conversation scores into a session score, (2) calls CALL RedDust.refresh_soul_score_snapshot(user_id, session_id) to update the user's rolling soul score, (3) calls preference_batch_extractor.extract_preferences_from_session(session_id, user_id, pool) for end-of-session preference sweep. This job is enqueued at session end as a fire-and-forget ARQ task. |
| Why we need it | Soul score computation is deliberately moved off the hot path. At WebSocket disconnect, the server must respond quickly — it cannot spend 5–10 seconds running LLM calls. ARQ (backed by Redis) handles this asynchronously. The job runs after the session ends, ensuring the database is always up to date without delaying the disconnect flow. The stored procedures (refresh_session_dimension_scores, refresh_soul_score_snapshot) are part of Rajanya's DB work. |
| How to verify | Enqueue job manually via ARQ CLI → job runs → session_dimension_score rows populated → user_soul_score_snapshot updated → v_user_dashboard_soul_score returns correct scores. |
| Files | backend/app/worker.py |
| Notes | Blocked on: stored procedures being defined in the DB schema (Step 9), and Redis being available for ARQ. For local development, run Redis via Docker: docker run -d -p 6379:6379 redis. |

# Phase 10 — Session Lifecycle

Steps 25–26 | Status: PENDING

### Step 25: Session Start Handler

| Step | 25 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | On WebSocket connect: (1) create app_user row if first session (upsert on user_id), (2) create user_session row with status='active', started_at=now(), (3) create first conversation row with sequence_no=1, started_at=now(), (4) call handle_fetch_user_context() and inject the returned context into the Gemini Live session system prompt or initial tool result, (5) initialise segment_index counter and turn_no counter in session state (in-memory, passed to the relay loop). |
| Why we need it | A clean session start ensures every downstream operation has valid FK references. transcript_segment rows need a valid session_id and conversation_id to insert — if these rows don't exist, every transcript write will fail with a foreign key violation. Injecting user context at session start is what makes Syan sound like it knows the user from the first word — not after the first tool call. |
| How to verify | Connect test WebSocket → user_session row created in DB, conversation row created, Gemini Live session initialised with user context injected. No FK violation errors on subsequent transcript writes. |
| Files | backend/app/api/ws_session.py |
| Notes | The Gemini Live session initialisation (how to inject context into the system prompt) depends on the Gemini Live SDK version. Check the google-genai SDK docs for the correct session config parameter. |

### Step 26: Session End Handler + Integration Test

| Step | 26 of 26 |
| --- | --- |
| Status | PENDING |
| What to do | On WebSocket disconnect: (1) mark conversation ended_at=now(), (2) mark user_session ended_at=now(), status='completed' (or 'abandoned' if zero turns), (3) call score_conversation_dimensions() for the final conversation (async task), (4) enqueue ARQ job compute_session_soul_score(user_id, session_id) — fire-and-forget, do NOT await, (5) call extract_preferences_from_session() as asyncio task. Write integration test: scripts/test_full_session.py — simulates WebSocket connect → 3 mock transcript segments → 1 music recommendation request → disconnect. Verifies: user_session row, conversation row, 3 transcript_segment rows, preference_extraction_log entries, music_recommendation row, music_track upsert, conversation_dimension_score rows, ARQ job enqueued. |
| Why we need it | The disconnect handler closes the loop on a session. Without it, sessions are never marked completed, soul score jobs are never enqueued, and preference batch extraction never runs. The integration test is equally important — it is the first time every component is tested together in sequence. It will catch FK failures, missing table columns, incorrect pool usage, and import errors that unit tests miss. |
| How to verify | Disconnect test WebSocket → user_session.ended_at set, status='completed', ARQ job visible in Redis queue. python scripts/test_full_session.py → all assertions pass. |
| Files | backend/app/api/ws_session.py, backend/app/worker.py, backend/scripts/test_full_session.py |
| Notes | The disconnect handler must return immediately — every awaited call here delays the WebSocket close. All heavy work must be fire-and-forget via asyncio.create_task or ARQ. The integration test is the final acceptance gate before the backend is declared ready for audio relay integration with Anirban. |

Summary Checklist

| # | Step | Phase | Status |
| --- | --- | --- | --- |
| 1 | Install RAG Dependencies | RAG | ✓ Done |
| 2 | File Parser Layer | RAG | ✓ Done |
| 3 | Embedding Pipeline | RAG | ✓ Done |
| 4 | pgvector Table Setup on Supabase | RAG | ✓ Done |
| 5 | Vector Search / Retriever | RAG | ✓ Done |
| 6 | Reranker (Present but Bypassed) | RAG | ✓ Done |
| 7 | Synthesizer (Response Formatter) | RAG | ✓ Done |
| 8 | End-to-End RAG Pipeline Wiring | RAG | ✓ Done |
| 9 | Core PostgreSQL Schema Migration | DB Schema | ⏳ Pending |
| 10 | asyncpg Connection Pool | DB Schema | ⏳ Pending |
| 11 | Function Call Dispatcher | Function Handlers | ✓ Done |
| 12 | get_music_recommendation Handler (Basic) | Function Handlers | 🔵 Current |
| 13 | fetch_user_context Handler | Function Handlers | ⏳ Pending |
| 14 | Additional Tables Migration | Schema Additions | ⏳ Pending |
| 15 | Schema Connectivity Verification | Schema Additions | ⏳ Pending |
| 16 | Per-Turn Preference Extractor | Pref. Extraction | ⏳ Pending |
| 17 | End-of-Session Batch Preference Extractor | Pref. Extraction | ⏳ Pending |
| 18 | Track Verifier (YouTube Data API) | Track Search | ⏳ Pending |
| 19 | YouTube API Key Setup & Cache Verification | Track Search | ⏳ Pending |
| 20 | Context-Aware Music Recommender | Music Engine | ⏳ Pending |
| 21 | Update Music Handler to Use Recommender | Music Engine | ⏳ Pending |
| 22 | Transcript Writer | Transcript Storage | ⏳ Pending |
| 23 | Conversation Dimension Scorer | Soul Score | ⏳ Pending |
| 24 | ARQ Job: Session Soul Score Computation | Soul Score | ⏳ Pending |
| 25 | Session Start Handler | Session Lifecycle | ⏳ Pending |
| 26 | Session End Handler + Integration Test | Session Lifecycle | ⏳ Pending |

RedDust Backend Roadmap  •  Deadline: 4 September 2026  •  Internal Use Only