## Assumptions
RedDust MVP - Cost Optimization Analysis
STAFFING ASSUMPTIONS
Parameter | Original | Optimized | Notes
Senior Tech Lead - Hourly Rate | 72.5 | 60 | Offshore talent pool optimization
Mid Level Dev - Hourly Rate | 40 | 40 | Fair market rate, keep stable
AI/ML Dev - Hourly Rate | 40 | 40 | Fair market rate, keep stable
QA Engineer - Hourly Rate | 30 | 30 | Tool-heavy + automation focus
Marketer - Hourly Rate | 30 | 28 | Lean/organic focus
Senior Tech Lead - FTE | 0.5 | 0.5 | Consistent
Mid Level Full Stack - FTE | 2 | 1.5 | Reduce to lean MVP team
AI/ML Dev - FTE | 1 | 0.75 | Optimize for batch tasks
QA Engineer - FTE | 1 | 0.5 | Automation-first, part-time
Marketer - FTE | 0.5 | 0.5 | Lean organic + content
DISCOUNT ASSUMPTIONS
Scenario | Anodiam Discount % | Cloud Credits | Total Discount | Notes
Best Case (Optimistic) | 50% | 20% | 65% | Max discount + credits
Base Case (Realistic) | 25% | 15% | 37% | Conservative estimate
Worst Case (Conservative) | 0% | 0% | 0% | No discounts (contingency)
INFRASTRUCTURE ASSUMPTIONS
Service | Original | Optimized | Notes
LLM Tokens (Claude) | 1000 | 600 | Sonnet + Haiku + batch processing
Audio/Speech APIs | 700 | 700 | Deepgram optimization + monitoring
YouTube Music API | 400 | 250 | Caching + official embeds
Cloud Infrastructure | 600 | 350 | Serverless (Cloud Run/Lambda)
Marketing & User Acq | 1000 | 500 | Organic-first + low-cost channels
Service | Previous Optimized | New Cheaper Target | Key Changes & Rationale (June 2026)
LLM Tokens | 600 | $300–$400 | Switch primary usage to Grok (very cheap: ~$0.20–$0.50/M tokens), Gemini Flash ($0.50–$1.25/M), or Claude Haiku only for high-quality needs. Heavy use of batch processing, prompt caching (up to 50–90% savings), and routing cheaper models for simple tasks (mood analysis, basic recommendations).
Audio/Speech APIs | 700 | $350–$450 | Use Deepgram (strong value at ~$0.004–$0.008/min) or cheaper alternatives like AssemblyAI / Gladia / OpenAI Whisper-based options. Optimize by limiting mood detection frequency and using batch processing.
YouTube Music API / Integration | 250 | $100–$150 | Core YouTube Data API is mostly free (quota-based). This budget now covers only proxy/streaming buffers + caching. Consider supplementing with free/open embeds or cheaper music APIs where licensing allows.
Cloud Infrastructure | 350 | $150–$250 | Full serverless (AWS Lambda / GCP Cloud Run) + heavy use of startup credits. Spot instances for any GPU needs. Minimal always-on resources for 500 beta users.
Marketing & User Acquisition | 500 | $200–$300 | Strong organic-first focus: Reddit, Product Hunt, AI/music communities, content (TikTok/Instagram reels), referral programs. Minimal paid testing only on high-ROI channels.
Service | Monthly Cost (Au$) | Notes
LLM Tokens | $80 – $120 | Grok Fast / Gemini Flash + heavy caching
Audio/Speech APIs | $80 – $150 | Much lower volume
YouTube Music Integration | 0 | Still fully free
Cloud Infrastructure | $80 – $150 | Serverless, even lower usage
Marketing & User Acquisition | $100 – $200 | Lower ad testing budget
Total Monthly Infrastructure | $340 – $620 | Very lean

## MVP
DETAILED COST BREAKDOWN - 3 SCENARIOS
SCENARIO 1: BEST CASE (Aggressive Optimization)
Cost Category | Unit | FTE | Au$/hour | Total
Senior Full Stack | hours/month | 2 | 75 | 24000
AI/ML Dev | hours/month | 2 | 40 | 12800
Marketer | hours/month | 1 | 28 | 4480
Subtotal - Staffing (Gross) |  |  |  | 41280
INFRASTRUCTURE
LLM Tokens (Grok/Gemini) |  |  |  | 100
Audio/Speech APIs (Deepgram) |  |  |  | 120
YouTube API (Cached) |  |  |  | 0
Cloud Infrastructure (Serverless) |  |  |  | 120
Subtotal - Infrastructure |  |  |  | 340
TOTAL MONTHLY BURN |  |  |  | 41620
6-MONTH TOTAL INVESTMENT |  |  |  | 249720

## First 6 months
DETAILED COST BREAKDOWN - 3 SCENARIOS
SCENARIO 1: BEST CASE (Aggressive Optimization)
Cost Category | Unit | FTE | Au$/hour | Total
Senior Full Stack | hours/month | 2 | 75 | 24000
AI/ML Dev | hours/month | 2 | 40 | 12800
Marketer | hours/month | 1 | 28 | 4480
Subtotal - Staffing (Gross) |  |  |  | 41280
INFRASTRUCTURE
LLM Tokens (Grok/Gemini) |  |  |  | 100
Audio/Speech APIs (Deepgram) |  |  |  | 120
YouTube API (Cached) |  |  |  | 0
Cloud Infrastructure (Serverless) |  |  |  | 120
Subtotal - Infrastructure |  |  |  | 340
TOTAL MONTHLY BURN |  |  |  | 41620
6-MONTH TOTAL INVESTMENT |  |  |  | 249720

## Scenario_Comparison
SCENARIO COMPARISON - 3 OPTIONS
Metric | Best Case | Base Case | Worst Case
Monthly Staffing (Gross) | 11400 | 12600 | 13650
Anodiam Discount % | 50% | 25% | 0%
Staffing Cost (After Discount) | 5700 | 9450 | 13650
Infrastructure Gross | 2600 | 2900 | 3700
Cloud Credits % | 15% | 10% | 0%
Infrastructure (After Credits) | 2210 | 2610 | 3700
TOTAL MONTHLY BURN | 7910 | 12060 | 17350
6-Month Investment | 47460 | 72360 | 104100
Cost per User/Month | 1582% | 2412% | 3470%
Savings vs Original | 71340 | 46440 | 14700
% Improvement | 6000% | 3900% | 1240%

## Phased_Rollout
PHASED ROLLOUT STRATEGY - VALIDATION APPROACH
Phase | Duration | Beta Users | Monthly Burn | 6-Month Total | Key Milestone
Phase 1: Validation | 2 months | 50 | 7910 | 15820 | Validate core assumptions
Phase 2: Growth | 2 months | 200 | 8500 | 17000 | Scale to 200 users
Phase 3: Ramp | 2 months | 500 | 12060 | 24120 | Full MVP target
TOTAL 6-MONTH INVESTMENT (Phased) |  |  |  | 56940
VALIDATION METRICS TO TRACK
• Cost per active user (track weekly)
• LLM token spend per session (optimize prompts)
• Cloud infrastructure cost (monitor scaling)
• User acquisition cost (determine channel ROI)
• API call distribution (identify optimization targets)
• Server latency & cost correlation

## Cost_Monitoring
COST MONITORING & OPTIMIZATION CHECKLIST
WEEK 1-2: SETUP
☐ Set up cost tracking in Cloud Console (AWS/GCP)
☐ Configure billing alerts (threshold: 150% of budget)
☐ Create dashboard: spend by service/team
☐ Establish per-user cost baseline
☐ Document API quota limits & scaling triggers
WEEK 3-4: OPTIMIZATION
☐ Implement Claude batch processing (50% savings)
☐ Switch non-critical features to Haiku (50% cheaper)
☐ Configure prompt caching (20-30% token reduction)
☐ Apply startup credits to cloud provider
☐ Set up automated scaling (scale down off-peak)
ONGOING: MONTHLY REVIEWS
☐ Review actual spend vs. budget (+/- 10% variance)
☐ Identify highest-cost users/features
☐ Renegotiate Anodiam discount if possible
☐ Evaluate cheaper LLM alternatives (Grok, Llama)
☐ Audit for unused APIs or services
☐ Cost per user trend (should decrease with scale)